## List
OrganizationIDfromAT | Participant | Program Type | Type | Workflow Specialist | Project Manager | Hand off | Invite Date | Invite Accepted | Visit Date | Draft Sent with PNP and Portal Forms | Follow Up Required | Draft Complete | Final Draft Complete Including Portal | Live with Portal | 3-Month Notice | 3-Month Visit | 9-Month | EMR
#N/A | 5 City Regional F&R Grant | HIE | Community Provider | Ed/Chuck | Brett | 2016-08-10 | 2016-08-11 |  | 2016-09-26
#N/A | A New Leaf | SHIP | Behavioral Health | Ed/Lee | Angell | 2016-07-01 | 2016-07-07 |  | 2016-08-25 | [8 empty] | NextGen (w/Topaz)
#N/A | Abrazo Community Health Network (ACO) | HIE | Hospital |  | Brett | N/A | N/A |  | 2016-07-21 | 2016-07-21 |  | 2016-07-22 | 2016-07-22 |  |  |  |  | Cerner/Athena
O000017 | Abrazo Medical Group | HIE | Provider | Chuck | Brett | N/A | 2016-04-20 |  | 2016-05-11 | 2016-05-16 |  | 2016-07-01 | 2016-07-07 |  |  |  |  | Athena Health
O000022 | Adelante | HIE | FQHC | N/A | Ted | N/A | N/A |  | N/A | N/A | [7 empty] | NextGen
O000062 | AHCCCS | HIE | Payer | Chuck | Brett | 2016-06-29 | 2016-06-29 |  | 2016-07-05 | 2016-07-07 |  | 2016-07-12 | 2016-07-12 |  |  |  |  | NA
O000047 | Angela Wyatt Dermatology | HIE | Specialty | Ed | Brett | 2016-04-22 | 2016-05-06 |  | 2016-06-01 | 2016-06-03 |  | 2016-07-15 | 2016-07-15 |  |  |  |  | Athena Health
O000055 | Arizona Community Physicians | HIE | Provider | Chuck | Brett | 2016-02-29 | 2016-02-29 |  | 2016-03-22 | 2016-03-30 |  | 2016-03-30 | 2016-03-30 |  |  |  |  | Allscripts
O000056 | Arizona Connected Care | HIE | ACO | Chuck | Brett | 2016-02-22 | 2016-02-29 |  | 2016-03-15 | 2016-03-24 |  | 2016-04-19 | 2016-06-28 |  |  |  |  | NA
#N/A | Arizona Counseling & Treatment Services | SHIP | Behavioral Health | Ed | Angell | 2016-04-18 | 2016-04-18 |  | 2016-05-10 | 2016-05-11 |  | 2016-05-25 | 2016-05-26 |  |  |  |  | ClaimTrack
O000059 | Arizona Family Care | HIE | Provider | Chuck | Brett | 2016-03-16 | 2016-03-16 |  | 2016-07-26 | Organizational Hold | [7 empty] | Practice Partner
#N/A | Arizona Kidney Disease & Hypertension Centers | HIE | Specialty | Chuck | Brett | 2016-02-25 | 2016-02-25 |  | 2016-03-09 | 2016-03-10 |  | 2016-03-16 | 2016-03-21 |  |  |  |  | AthenaDoctalk
O000067 | Arizona Pain Specialists | PII | Specialty | Chuck | Catelyn | 2016-05-02 | 2016-05-05 |  | 2016-07-25 | 2016-07-28 | On Hold for Org | [6 empty] | Aprima
#N/A | Arizona Youth and Family Services | HIE | Behavioral Health | Ed/Lee | Angell | 2016-07-08 | 2016-07-12 |  | 2016-08-23 | 2016-08-24 | [7 empty] | NextGen (w/Topaz)
#N/A | Arizona's Children Association | SHIP | Behavioral Health | Ed | Moorthi | 2016-04-20 | 2016-05-09 |  | 2016-06-29 | 2016-07-08 |  | 2016-08-24 | 2016-08-24 |  |  |  |  | Practice Partner
O000083 | ASAP Health Solutions | HIE | Provider | Chuck/Ed/Lee | Brett | 2016-06-10 | 2016-06-13 |  | 2016-07-26 | 2016-07-28 |  | 2016-08-15 | 2016-08-15 |  |  |  |  | eMDs
#N/A | Assurance Health & Wellness | PII/SHIP | Behavioral Health | Chuck | Catelyn | 2016-02-25 | 2016-02-25 |  | 2016-03-15 | 2016-03-23 |  | 2016-03-30 | 2016-03-30 |  |  |  |  | NextGen
O000092 | AZDHS | HIE | State and Local Gov't | N/A | Ted | N/A | N/A |  | N/A | N/A |  | N/A | N/A
O000113 | Banner Health Ambulatory | HIE | Provider | N/A | Ted | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  |  |  |  | Cerner
O000113 | Banner Health University Campuses | [16 empty] | Epic
O000113 | Banner Tucson | HIE | Hospital | N/A | Brett | N/A | N/A |  | N/A | N/A |  | N/A | N/A
O000123 | Barnett Dulaney Perkins Eye Center | HIE | Specialty | Chuck | Jaime | N/A | N/A |  | 2016-03-30 | 2016-04-07 |  | 2016-04-18 | [5 empty] | NextGen
O000124 | Bart Carter, MD | HIE | Provider | Chuck | Brett | 2016-02-08 | N/A |  | 2016-02-24 | 2016-03-03 |  | Delayed | [5 empty] | Amazing Charts
#N/A | Bayada Home Health Care | HIE | Home Health | Ed | Brett | 2016-07-13 | 2016-07-15 |  | 2016-09-07
#N/A | Bayless Healthcare Group | PII/SHIP | Behavioral Health | Chuck | Catelyn | 2016-03-10 | N/A |  | 2016-03-23 | 2016-03-31 |  | 2016-04-28 | 2016-06-02 |  |  |  |  | Credible
#N/A | Beech Medical Group, Inc. | HIE | Home Health | Ed | Brett | 2016-05-10 | 2016-05-11 |  | 2016-06-09 | 2016-06-14 |  | 2016-06-21 | 2016-06-21 |  |  |  |  | Credible
O000136 | Benson Hospital | HIE | CAH | Chuck | Brett | N/A | N/A |  | 2/4/2016, 8/9/16 | 2016-08-10 | [5 empty] | N/A |  | HMS
O000136 | Benson Hospital - HIE Tools | HIE | CAH | Chuck | Brett |  | 2016-06-02 |  | 2016-08-09 | N/A | [5 empty] | N/A |  | MedHost/ReDoc
O000152 | Bridgeway | HIE | Health Plan | Chuck | Brett | N/A | N/A |  | 2016-02-09 | 2016-02-18 |  | 2016-03-01 | 2016-03-08 | Operztionnal | 2016-08-07 | 2016-09-01 |  | NA
#N/A | Canyonlands Healthcare | PII | FQHC | Chuck | Catelyn | 2016-01-19 | 2016-01-19 |  | 2016-03-29 | 2016-04-06 |  | 2016-05-31 | 2016-06-06 | Operational | 2016-08-07 | 2016-09-08 |  | NextGen(w/Topaz)
O000172 | Care1st | HIE | Health Plan |  | Jaime | [10 empty] | N/A
O000173 | Carondelet | [16 empty] | Cerner
#N/A | Casa De Los Ninos | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-08 | 2016-07-11 |  | 2016-07-26 | 2016-07-27 |  | 2016-08-02 | 2016-08-02 |  |  |  |  | Avatar
#N/A | Catalina Pointe Arthritis and Rhumatology | HIE | Provider | Chuck | Brett | 2016-08-09 | 2016-08-09 | 2016-08-11 | 2016-10-05 | [8 empty] | eCW
O000185 | Cenpatico | HIE | RHBA | Chuck | Brett | 2016-03-07 |  |  | 2016-03-22 | 2016-03-31 |  | 2016-04-12 | 2016-04-13 |  |  |  |  | NA
O000200 | Chicanos Por La Causa | PII/SHIP | Behavioral Health | Chuck/Ed/Lee | Catelyn | 2016-06-09 | 2016-06-10 |  | 2016-08-22 | 2016-08-23 | [7 empty] | Claim Track
#N/A | Child and Family Support Services | SHIP | Behavioral Health | Ed | Moorthi | 2016-07-15 | 2016-07-19 | New Dates Sent 8/19 | 2016-09-01
O000203 | Childrens Clinics Rehabilative Services of Tucson | PII | Specialty | Chuck | Catelyn | 2016-02-22 | 2016-02-24 |  | 2016-03-15 | 2016-03-28 |  | Delay | [5 empty] | NextGen
O000211 | Chiricahua Community Health Center | PII | FQHC/PII | Chuck | Catelyn | 2016-07-07 | 2016-07-07 |  | 2016-08-31 | [8 empty] | NextGen
#N/A | Christopher Moor, MD | HIE | Provider | Chuck | Chuck | 2016-05-26 | 2016-05-26 |  | N/A | 2016-05-26 |  | 2016-05-31 | 2016-06-01 |  |  |  |  | Epic
O000218 | Cigna Medical Group | HIE | Health Plan | Ed/Chuck/Lee | Brett | 2016-06-17 | 2016-06-17 |  | 2016-06-27 | 2016-06-28 | 2016-08-08 | [6 empty] | Allscripts
#N/A | Circle the City | SHIP | Behavioral Health | Ed | Moorthi | 2016-08-03 | 2016-08-26
#N/A | City of Buckeye Fire and Rescue |  | City Government | Ed | Brett | 2016-08-23 | 2016-08-24 | 2016-08-15 | 2016-10-11
#N/A | City of Surprise Fire and Rescue (Direct and A&N) | HIE |  |  | Brett | N/A | N/A |  | 2016-05-24 | 2016-06-02 | 2016-07-19 | [6 empty] | EOS
#N/A | City Surprise Fire and Rescue (Portal) | HIE | State and Local Gov't | Chuck | Angell | 2015-12-14 | 2015-12-21 |  | 2015-12-29 | 2016-01-04 |  | 2016-01-11 | 2016-01-13 |  |  | 2016-05-24 |  | EOS
O000230 | Cobre Valley Medical Group | HIE | Providers | Chuck | Angell | 6/23/16 | 2016-06-24 |  | 2016-07-27 | 2016-08-01 | [7 empty] | NextGen
#N/A | Cobre Valley Regional Medical Center | HIE | CAH | Chuck | Angell | N/A | N/A |  | 2016-03-08 | 2016-03-21 |  | 2016-05-13 | 2016-05-13 |  | 2016-07-27 |  |  | Meditech
#N/A | CODAC Health Recovery Wellness, Inc. | SHIP | Behavioral Health | Chuck | Moorthi | 2016-03-07 | 2016-03-07 |  | 2016-03-15 | 2016-03-23 |  | 2016-03-31 | 2016-04-01 | Operational | 2016-08-07 |  |  | NextGen
#N/A | Colorado River Pediatrics | HIE | Specialty Provider | Chuck | Brett | 2016-08-10 | 2016-08-10 |  | 2016-09-21 | [8 empty] | SuiteMed IMS
O000237 | Commonwealth ACO | HIE | ACO | Chuck | Brett | 2016-01-05 | 2016-01-05 |  | 2016-01-14 | 2016-01-22 |  | Delayed | [5 empty] | eVigils
#N/A | Community Bridges | PII/SHIP | Behavioral Health | Ed/ Lee | Catelyn | 2016-07-07 | 2016-07-08 |  | 2016-08-03 | 2016-08-04 |  | 2016-08-19 | Hold for Portal Request |  |  |  |  | NextGen
#N/A | Community Health Associates (Yuma) | SHIP | Behavioral Health | Chuck | Moorthi | 2016-03-31 | 2016-04-01 |  | 2016-04-19 | 2016-04-25 | Hold for BH Portal Data | 2016-04-28 | 2016-04-28 |  |  |  |  | Avatar
O000244 | Community Medical Servies | OTP | Behavioral Health | Lee | Brett | 2016-06-10 | 2016-06-13 |  | 2016-07-26 | 2016-07-28 | 2016-08-23 | [6 empty] | Methasoft
O000245 | Community Partners Inc | HIE | Behavioral Health | Ed/Lee | Angell | 2016-05-18 | 2016-05-19 |  | 2016-06-29 | 2016-06-30 | 2016-07-19 | 2016-07-25 | 2016-07-25 |  |  |  |  | Treat
O000246 | Community Provider of Enrichment Services | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-01 | 2016-07-05 |  | 2016-09-07 | [8 empty] | Claim Track
O000251 | Connections AZ | PII/SHIP | Behavioral Health | Ed | Catelyn | 2016-05-26 | 2016-05-31 |  | 2016-07-13 | 2016-07-14 |  | 2016-07-18 | 2016-07-18 |  |  |  |  | NextGen/Credible
O000256 | Cope Community Services | SHIP | Behavioral Health | Ed | Moorthi | 2016-05-10 | 2016-05-10 |  | 2016-06-22 | 2016-06-24 | 2016-07-19 | [6 empty] | HIMS
#N/A | Corazon Integrated Healthcare Services | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-13 | 2016-07-14 |  | 2016-08-24
#N/A | Creative Care | HIE | SNF | Chuck/Ed/Lee | Brett | 2016-06-06 | Reminder 7/18/16 | [10 empty] | ESC
O000266 | Crossroads Mission | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-01 | 2016-07-05 |  | 2016-08-30
#N/A | Desert Kidney Associates | HIE | Specialty | Chuck | Brett | 2015-12-16 | 2015-12-16 |  | 1/5/2016, 1/11/2016 | 2016-01-21 |  | 2016-02-05 | 2016-02-17 |  |  |  |  | eVigils
O000293 | Desert Senita | PII/SHIP | FQHC | Chuck | Catelyn | 2016-01-07 | 2016-01-07 |  | 2016-01-25 | 2016-01-26 |  | 2016-02-02 | 2016-02-19 |  |  |  |  | NI
O000294 | Desert Spine Institute (EPIC) | HIE | Specialty Care | Chuck | N/A | 2016-07-01 | N/A |  | N/A | 2016-07-05 | [7 empty] | Epic/YRMC
O000311 | Dignity Health | HIE | Payer | N/A | Angell | 2016-03-21 | N/A |  | N/A | N/A |  | N/A | N/A |  |  |  |  | Cerner/Allscripts
O000313 | District Medical Group | PII | Provider | Chuck | Catelyn | 2016-01-27 | 2016-01-27 |  | 2016-03-01 | 2016-03-07 |  | 2016-05-02 | 2016-05-02 | Operational | 2016-08-07 |  |  | GE Centricity
O000316 | Dorothy L Wong Medical Office (EPIC) | HIE |  | Chuck | Chuck | 2016-05-18 | N/A |  | N/A | 2016-06-02 |  | 2016-07-01 | 2016-07-05 |  |  |  |  | Epic
#N/A | East Flagstaff Family Medicine | HIE-e-vigils | Provider | Chuck | Brett | 2016-01-05 | 2016-01-05 |  | 2016-01-13 | 2016-01-21 |  | 2016-02-22 | 2016-02-25 |  |  |  |  | Greenway
O000146 | Easter Seals | SHIP | Behavioral Health | Chuck/Ed/Lee | Moorthi | 2016-06-17 | 2016-06-17 |  | 2016-07-20 | Hold for BH Portal Data | [7 empty] | HIMS
O000341 | El Rio | Refferal | FQHC | Tony | Jaime | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  |  |  |  | NextGen(w/Topaz)
#N/A | El Rio Health Center | SHIP | FQHC | Chuck/Ed/Lee | Moorthi | 2016-05-26 | 2016-05-27 |  | 2016-06-01 | 2016-06-02 |  | 2016-06-27 | 2016-06-27 |  |  |  |  | NextGen
#N/A | Enticare | HIE | Specialty | Ed | Brett | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-09-27
#N/A | Family Involvement Center | SHIP | Behavioral Health | Ed | Moorthi | 2016-08-10 | 2016-08-12 | [10 empty] | ConnectOne Platform by Progression Systems
#N/A | Family Service Agency | HIE | Behavioral Health | Ed/Lee | Brett | 2016-07-08 | 2016-07-12 |  | 2016-08-11 | 2016-08-15 | [7 empty] | Claim Track
#N/A | Flagstaff Schildren's Clinic | [16 empty] | Cerner
#N/A | Flagstaff Surgical Associates | HIE | Specialty | Chuck | Angell | 2016-04-13 | 2016-04-13 |  | 2016-04-27 | Never signed agreement
O000377 | Foundation for Senior Living | HIE | Home Care | Ed/Lee | Brett | 2016-07-01 | 2016-07-07 |  | Delayed by ORG | [8 empty] | Claim Track
O000395 | Gila Health | HIE | Provider | Chuck | Brett | 2016-03-16 | 2016-03-16 |  | 2016-04-12 | 2016-04-18 |  | 2016-07-06 | 2016-07-07 |  |  |  |  | e-MD
#N/A | Gila Valley Clinic | HIE | Provider | Chuck | Brett | 2016-01-21 | 2016-02-08 |  | 2016-02-24 | 2016-03-03 |  | 2016-03-04 | 2016-03-09 |  | Not Ready BR 6/2 |  |  | eCW
O000439 | Health Choice (HCA) | HIE | Health Plan | Chuck | Brett | 2015-12-15 | 2015-12-15 |  | 2016-01-11 | 2016-01-22 |  | 2016-02-05 | 2016-02-08 |  |  | N/A |  | NA
O000439 | Health Choice (HCE) | HIE | Health Plan | Chuck | Brett | N/A | N/A |  | 2016-03-21 | 2016-04-20 |  | 2016-05-09 | 2016-05-12 |  |  |  |  | NA
O000439 | Health Choice (VBP) | Referral HC | Health Plan | Chuck | Brett | N/A | N/A |  | 2016-04-20 | 2016-05-12 |  | 2016-05-12 | 5/1216 |  |  |  |  | NA
O000439 | Health Choice High ER | Referral HC | Health Plan | Ed | Brett | N/A | N/A |  | 2016-05-19 | 2016-05-26 |  | 2016-06-13 | 2016-06-13 |  |  |  |  | NA
O000439 | Health Choice Integrated Care | HIE | RHBA | Chuck | Brett | 2016-01-27 | 2016-01-27 |  | 2016-03-02 | 2016-03-21 |  | 2016-04-18 | 2016-04-21 |  |  |  |  | NA
O000441 | Healthcare for the Homeless | PII | FQHC | Chuck | Catelyn | 2015-12-22 | 2015-12-23 |  | 2016-01-28 | 2016-01-28 |  | 2016-02-22 | 2016-02-19 | Operational | 2016-08-07 |  |  | eCW
#N/A | HealthNet/Bridge | HIE | Health Plan | Chuck | Brett | 2015-02-16 | 2016-02-16 |  | 2016-03-08 | 2016-03-16 |  | 2016-04-04 | 2016-04-04 |  |  |  |  | NA
O000444 | Heart and Vascular Center of Arizona | HIE | Specialty | Chuck | Angell | 2016-03-23 | 2016-03-23 |  | 2016-03-30 | 2016-04-07 |  | Delayed | [5 empty] | GE Centricity
#N/A | Helping Associates Inc. | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-25 | 2016-07-25 | 2016-07-27 | 2016-09-27 | [8 empty] | Pace Plus
O000447 | Helping Hearts Residential Facility | HIE | Behavioral Health | Ed/Lee | Brett | 2016-07-01 | 2016-07-07 |  | 2016-08-02 | 2016-08-04 | Hold for BH Portal Data
#N/A | Home Health Insights, Inc. | HIE | Home Health | Ed | Angell | 2016-03-10 | 2016-04-21 |  | 2016-05-17 | 2016-05-18 |  | 2016-06-20 | 2016-06-20
#N/A | Homewood Family Physicians | HIE | Provider | Chuck | Angell | 2016-01-13 | 2016-02-17 |  | 2016-03-08 | 2016-03-21 |  | 2016-03-31 | 2016-04-06 |  |  |  |  | NI
O000458 | HonorHealth | [16 empty] | Epic
O000460 | Hope Inc. | SHIP | Behavioral Health | Chuck/Ed/Lee | Moorthi | 2016-05-27 | 2016-05-31 |  | 2016-08-02 | 2016-08-04 | 2016-08-23 | [6 empty] | HMS
O000463 | Horizon Health and Wellness | PII/SHIP | Behavioral Health | Ed | Catelyn | 2016-04-05 | 2016-04-21 |  | 2016-05-31 | 2016-06-02 |  | 2016-06-20 | 2016-06-20 |  |  |  |  | ClaimTrack
#N/A | Human Services Consultants | HIE | Behavioral Health | Ed | Angell | 2016-07-15 | 2016-07-19 |  | 2016-09-27
O000473 | Iasis Health | HIE | Hospital | Chuck | Angell | 2016-03-24 | N/A |  | N/A | N/A |  | N/A | N/A |  |  |  |  | McKesson
#N/A | Intermountain Centers for Human Devel | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-08 | 2016-07-11 |  | 2016-08-24 | 2016-08-29 | [7 empty] | NetSmart- My Evolv
O000506 | Jewish Family Childrens Services | PII/SHIP | Behavioral Health | Ed | Catelyn | 2016-04-22 | 2016-04-22 |  | 2016-07-20 | 2016-07-21 | 2016-08-08 | [6 empty] | NextGen/Topaz
O000701 | Kidney Resource Services (OPTUM ACO) | Referral Optum | ACO | Chuck | Angell | 2016-04-01 | 2016-04-01 |  | 2016-04-26 | 2016-05-10 | [7 empty] | NA
O000535 | Kingman Regional Medical Center | HIE | Hospital | Chuck | Ted | N/A | N/A |  | 2016-03-14 | N/A |  | N/A | N/A |  |  | N/A
#N/A | La Frontera | SHIP | Behavioral Health | Chuck/Ed/Lee | Moorthi | 2016-06-10 | 2016-06-13 |  | 2016-07-06 | 2016-07-22 |  | 2016-07-27 | 2016-07-27 |  |  |  |  | Netsmart Avatar
#N/A | La Frontera-Empact | PII | Behavioral Health | Chuck/Ed/Lee | Catelyn | 2016-06-09 | 2016-06-10 |  | Rescheduled | [8 empty] | NextGen/topaz
O000547 | La Paz Regional Hospital | HIE | Hospital | Ed | Angell | 2016-04-14 | 2016-04-14 |  | 2016-05-25 | Organizational Hold | [7 empty] | CPSI
O000559 | LifeShare Management Group | SHIP | Behavioral Health | Ed | Moorthi | 2016-05-10 | 2016-05-10 |  | 2016-06-09 | 2016-06-14 | 2016-07-19 | 2016-07-19 | 2016-07-19 |  |  |  |  | Therap
#N/A | Lifewell Behavioral Wellness | PII | Behavioral Health | Ed | Catelyn | 2016-08-24 | 2016-08-29
#N/A | Little Colorado Behavioral Health Centers | SHIP | CAH | Chuck | Moorthi | 2016-07-01 | 2016-07-05 |  | 2016-09-14 | [8 empty] | HIMS
O000577 | Marana Health Center | SHIP | FQHC | Chuck | Moorthi | 2016-06-18 | 2016-06-20 |  | 2016-07-12 | 2016-07-14 | 2016-08-01 | [6 empty] | GE Centricity
O000578 | Marc Community Resources | PII/SHIP | Behavioral Health | Chuck/Ed/Lee | Catelyn | 2016-05-25 | 2016-05-26 |  | 2016-06-15 | 2016-06-20 | 2016-07-19 | 2016-08-01 | 2016-08-01 |  |  |  |  | NextGen(w/Topaz)
O000582 | Maricopa County Corrections | HIE | State and Local Gov't | Chuck | Jaime | 2016-02-11 | 2016-02-11 |  | 2016-03-09 | 2016-03-21 |  | 2016-06-01 | [5 empty] | Tech Care
O000583 | Maricopa Health Plan | HIE | Health Plan |  | Brett | [12 empty] | NA
O000587 | Mariposa CHC | HIE | FQHC |  | Brett | [12 empty] | NextGen
O000601 | MD24 | HIE | Provider |  | Brett | [10 empty] | N/A
#N/A | Med-Cure Internal Medicine | HIE | Provider | Chuck | Angell | 2015-12-22 | 2015-12-23 |  | 2016-01-06 | 2016-01-21 |  | 2016-02-05 | 2016-02-19 |  |  |  |  | NI
O000611 | Mentally Ill Kids In Distress | SHIP | Behavioral Health | Ed/Lee | Moorthi | 2016-07-01 | 2016-07-07 |  | 2016-09-20 | [8 empty] | Credible
O000612 | Mercy Care Plan | HIE | Health Plan |  | Brett | [12 empty] | NA
O000613 | Mercy Maricopa | HIE | RHBA |  | Brett | [12 empty] | NA
O000621 | MIHS | PII/SHIP | Hospital | Chuck | Catelyn | N/A | N/A |  | 2016-02-22 | 2016-03-03 |  | Delayed | [5 empty] | Epic
#N/A | Mohave Mental Healtlh Clinic | SHIP | Behavioral Health | Chuck | Moorthi | 2016-08-09 | 2016-08-09 | 2016-08-15 | 2016-09-19 |  | 2016-08-24
#N/A | Mount Graham Regional Medical Center | HIE | Hospital | Chuck | Ted | N/A | N/A |  | 2016-02-24 | 2016-03-07 |  | 2016-06-06 | 2016-06-08 | Operational | 2016-08-07 | 2016-09-13 |  | Meditech
O000637 | Mountain Park | PII | FQHC | Chuck | Catelyn | 2016-03-03 |  |  | 2016-03-23 | 2016-03-31 |  | draft to Keith | [5 empty] | eCW
O000638 | Mountain View Pediatrics | HIE | Specialty | Chuck | Jaime | 2016-03-23 | 2016-04-01 |  | 2016-04-27 | 2016-05-05 |  | 2016-05-31 | 2016-06-15 |  |  |  |  | Office Praticum
O000676 | NAH | HIE | Hospital |  | Ted
O000648 | Native American Connections | PII | Behavioral Health | Chuck/Ed/Lee | Catelyn | 2016-06-08 | 2016-06-08 |  | 2016-07-07 | 2016-07-08 | 2016-08-01 | 2016-08-05 | 2016-08-08 |  |  |  |  | HMS
O000649 | Native Health | PII/SHIP | FQHC | Chuck | Catelyn | 2016-03-14 | 2016-03-21 |  | 2016-03-30 | 2016-04-06 |  | 2016-04-26 | [5 empty] | RPMS(VA)
O000652 | NAZCARE | SHIP | Behavioral Health | Ed | Moorthi | 2016-05-02 | 2016-05-06 |  | 2016-06-07 | 2016-07-28 |  | 2016-08-04 | 2016-08-04 |  |  |  |  | Credible
#N/A | New Hope | SHIP | Behavioral Health | Ed/Lee | Moorthi | 2016-07-08 | 2016-07-11 |  | Rescheduled | [8 empty] | Paper
O000659 | New Pueblo Medicine | HIE | Provider | Chuck | Brett | 2015-12-16 |  |  | 2016-02-01 | 2016-02-03 |  | 2016-02-05 | 2016-02-05 |  | 2016-05-17 | 2016-06-14 |  | NextGen
#N/A | Nightengale Homecare | HIE | Home Care | Ed | Brett | 2016-07-25 | 2016-07-25 |  | 2016-09-06 | [8 empty] | Care Voyant
#N/A | NOAH | HIE | Provider | Ed/Lee | Brett | 2016-07-01 | 2016-07-07 |  | 2016-09-07 | [8 empty] | Epic
#N/A | North Country HealthCare | PII | FQHC | Chuck | Catelyn | 2015-12-01 |  |  | 2016-03-10 | 2016-03-21 |  | 2016-03-31 | 2016-04-06 |  |  |  |  | GE Centricity
O000684 | Northwest Neurospecialists | PII | Specialty | Ed | Catelyn | 2016-04-13 |  |  | 2016-05-18 | 2016-05-31 |  | 2016-06-30 | 2016-06-30 |  |  |  |  | NextGen
O000689 | Nursewise | SHIP | Specialty | Chuck/Ed/Lee | Moorthi | 2016-06-06 | 2016-06-07 |  | 2016-07-06 | 2016-07-15 | 2016-08-01 | [6 empty] | LVM
O000694 | Old Pueblo Community Services | HIE |  | Chuck/Lee | Angell | 2016-05-02 | 2016-05-05 |  | 2016-06-14 | 2016-06-20 |  | 2016-06-29 | 2016-07-07 |  |  |  |  | Claim Track
O000699 | Open Hearts Arizona | HIE | Behavioral Health | Chuck/Ed/Lee | Brett | 2016-06-17 | 2016-06-17 |  | 2016-07-19 | 2016-07-22 | 2016-08-08 | 2016-08-19 | 2016-08-20 |  |  |  |  | Credible
O000700 | Options Medical | HIE | Provider | Chuck | Brett | 2015-12-17 | 2015-12-21 |  | 2016-01-12 | 2016-01-21 |  | 2016-01-29 | 2016-02-09 |  |  |  |  | MAC Care
O000701 | OPTUM Medical Network | HIE | ACO | Chuck | Angell | 2015-12-15 | 2015-12-15 |  | 2015-12-23 | 2015-12-30 |  | 2016-01-07 | 2016-02-01 |  |  | 2015-12-01 |  | NA
O000708 | Page Family Practice | HIE | Provider | Chuck | Brett | 2016-01-05 | 2016-01-05 |  | 2016-01-14 | 2016-02-05 |  | 2016-02-12 | 2016-03-31 |  |  |  |  | NextGen/e-Vigils
O000714 | Palo Verde Family Care Inc. | HIE | Provideer | Ed/Lee | Angell | 2016-04-28 | 2016-05-05 |  | 2016-06-21 | 2016-06-24 | 7/19/2016, 8/1/16 | Delayed 10/1 | [5 empty] | Amazing Charts
O000721 | Partners in Recovery | PII/SHIP | Behavioral Health | Lee | Catelyn | 2016-06-09 | 2016-06-10 |  | 2016-06-28 | 2016-07-08 | 2016-08-08 | 2016-08-12 | 2016-08-12 |  |  |  |  | NextGen(w/Topaz)
#N/A | Pasadera (Merged with Community Bridges) | SHIP | Behavioral Health | Ed | Moorthi | 2016-04-22 | 2016-04-22 |  | 2016-05-17 | 2016-05-23 |  | 2016-06-06 | 2016-06-08 | Will be part of Community Bridges Implementation |  |  |  | NextGen
#N/A | Pathways of Arizona | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-15 | 2016-07-18 |  | 2016-08-09 | 2016-08-10 |  | 2016-08-26 | [5 empty] | Netsmart/Avatar
O000749 | Phoenix Children's Hospital | PII | Hospital | N/A | Catelyn | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  |  |  |  | Allscripts
O000754 | Phoenix Health Plan | HIE | Health Plan | Chuck | Jaime | 2016-02-17 |  |  | 2016-02-22 | 2016-02-23 |  | 2016-03-01 | 2016-03-07 |  |  |  |  | NA
#N/A | Phoenix Medical Group | PII | Provider | Ed | Catelyn | 2016-07-13 | 2016-07-15 |  | 2016-08-25 | 2016-08-26
O000957 | Phoenix Shanti Group | HIE | Provider | Chuck/Ed/Lee | Brett | 2016-04-19 | 2016-04-20 |  | 2016-05-24 | 2016-06-02 |  | 2016-06-10 | 2016-06-10 |  |  |  |  | NextGen
#N/A | Phoenix-Tucson Integrated Kidney Care | hie | Specialty | Chuck/Ed | Brett | 2016-08-10 | 2016-08-10 | 2016-08-12 | 2016-09-01
#N/A | PIMA County (Corrections) | HIE | State and Local Gov't | Chuck | Brett | 2015-12-23 | 2015-12-23 |  | 2016-01-27 | 2016-01-28 |  | 2016-02-16 | 2016-02-17 |  |  | N/A |  | Core
O000763 | Pima Heart | HIE | Specialty | Chuck | Angell | 2016-01-04 | 2016-01-04 |  | 2016-01-20 | 2016-01-22 |  | 2016-02-16 | 2016-03-08 |  |  |  |  | NI
O000765 | Pima Lung | HIE | Specialty | Chuck | Angell | 2015-12-21 | 2015-12-21 |  | 2016-01-04 | 2016-02-02 |  | 2016-02-04 | Delayed |  |  |  |  | NI
O000767 | Pinal Hispanic Council | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-01 | 2016-07-05 |  | 2016-08-24
O000772 | Plaza Healthcare | HIE | Provider | Chuck | Brett | 2016-01-15 | 2016-01-15 |  | 2016-02-03 | 2016-02-02 |  | 2016-02-05 | 2016-02-05 |  |  |  |  | Allscripts and Curapan
#N/A | PSA Behavioral Health | SHIP | Behavioral Health | Ed | Moorthi | 2016-07-18 | 2016-07-19 |  | 2016-09-15
O000805 | Recovery Innovations | SHIP | Behavioral Health | Chuck/Ed/Lee | Moorthi | 2016-05-26 | 2016-05-31 |  | 2016-07-12 | 2016-07-14 |  | 2016-08-08 | 2016-08-08 |  |  |  |  | Netsmart/Avatar
O000808 | Regional Center for Border Hlth | HIE | RHC | Chuck | Brett | N/A | N/A |  | 2016-02-10 | 2016-02-18 |  | n/a | n/a |  |  |  |  | NextGen
O000818 | Rio Rico Fire District | HIE | State and Local Gov't | Ed | Brett | 2016-03-21 | 2016-04-12 |  | 2016-05-03 | 2016-05-09 | 2016-07-19 | 2016-07-19 | 2016-07-25 |  |  |  |  | High Plains moving to Image Trends
O000819 | Rio Salado Behavioral Health System | HIE | Behavioral Health | Chuck | Brett | 2016-06-06 | 2016-06-07 |  | 2016-06-22 | 2016-06-27 |  | 2016-07-14 | 2016-07-14 |  |  |  |  | None
O000833 | Saguaro Surgical | HIE | Provider | Chuck | Ted | 2016-01-18 | 2016-04-21 |  | Delay | [8 empty] | Epic/TMC
O000839 | San Pedro Family Care | HIE | Provider | Chuck | Brett | 2016-01-15 |  |  | 2016-02-04 | 2016-02-05 |  | 2016-02-17 | 2016-02-17 |  | 2016-05-12 |  |  | eCW
O000840 | San Tan Behvioral Health Services | HIE | Behavioral Health | Ed/Lee | Brett | 2016-07-01 | 2016-07-07 |  | 2016-08-16 | 2016-08-20 | [7 empty] | Pace Plus
O000847 | Sante Operations | HIE | Home Care | Chuck | Jaime | N/A | N/A |  | 2016-04-07 | 2016-04-14 |  | 2016-04-20 | 2016-05-05 |  |  |  |  | Enterprise Wharehouse
O000881 | Sonoita-Elgin Fire District | HIE | State and Local Gov't | Chuck/Ed/Lee | Brett | 2016-06-17 | 2016-06-17 |  | 2016-08-30
O000883 | Sonoran Medical Centers | HIE | Provider | Ed/Lee | Brett | 2016-07-01 | 2016-07-07 |  | 2016-08-11 | 8/1516 | [7 empty] | NextGen
O000887 | Sound Physicians | HIE | Provider | Ed | Keith* | 2016-04-18 | 2016-04-18 |  | 2016-06-15 | 2016-06-20 | 7/19/2016, 8/1 | delayed | [5 empty] | NA
#N/A | Southeastern Arizona Behavioral Health Services, Inc. | SHIP | Behavioral Health | Ed | Moorthi | 2016-03-15 |  |  | 5/4/2016 -NS | 2016-05-10 |  | 2016-06-02 | 2016-06-02 |  |  |  |  | NextGen
O000889 | Southern Arizona Inf. Disease (part of TMC) | HIE | Specialty | Chuck | Ted | 2016-01-21 |  |  | 2016-02-16 | 2016-02-25 |  | Delayed | [5 empty] | EPIC
#N/A | Southwest Behavioral & Health Services | PII/SHIP | Behavioral Health | Chuck | Catelyn | 2016-03-31 | 2016-04-01 |  | 2016-04-20 | 2016-04-26 |  | 2016-06-02 | 2016-07-05 |  |  |  |  | HMS
#N/A | Southwest Network | PII/SHIP | Behavioral Health | Ed/Lee | Catelyn | 2016-07-07 | 2016-07-08 |  | 2016-08-16 | 2016-08-20 | [7 empty] | HMS
O000904 | Spectrum Healthcare Group | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-01 | 2016-07-05 |  | 2016-08-23 | [8 empty] | McKesson Paragon
O000907 | St. Elizabeth Health Centers | PII | FQHC | Chuck | Catelyn | 2016-07-01 | 2016-07-06 |  | 2016-07-26 | 2016-07-29 | 2016-08-23 | [6 empty] | GE Centricty-Quatres
O000924 | Sun Life Family Health Center. | HIE | FQHC | Chuck | Angell | 2016-03-01 |  |  | 2016-03-24 | 2016-04-06 |  | Delayed | [5 empty] | Planning e-Clinical Works
O000929 | Sunset Community Health Center | PII | FQHC | Chuck | Catelyn | N/A | N/A |  | 2016-02-10 | 2016-02-18 |  | 2016-03-01 | 2016-03-16 |  |  |  |  | NextGen
O000943 | Terros Behavioral Health Svcs | PII/SHIP | Behavioral Health | Chuck/Ed/Lee | Catelyn | 2016-06-09 | 2016-06-10 |  | 2016-08-03 | 2016-08-04 | 2016-08-23 | 2016-08-25 | 2016-08-25 |  |  |  |  | NextGen (w/Topaz)
#N/A | The Crossroads Inc. | SHIP | Behavioral Health | Ed | Moorthi | 2016-07-25 | 2016-07-25 |  | 2016-09-06 | [8 empty] | Kipu
#N/A | Thunderbird Internal Medicine | Referral OPTUM | HIE | Chuck | Brett | 2016-08-23 | 2016-08-24 | [5 empty] | N/A |  |  |  |  | eCW
O000966 | TMC | HIE | Hospital |  | Ted | [12 empty] | EPIC
O000966 | TMC One (part of TMC) | HIE | Provider |  | Ted | 2016-02-15 |  |  | 2016-02-16 | 2016-02-18 |  | On Hold | On Hold |  |  |  |  | EPIC
#N/A | Touchstone Behavioral Health | PII/SHIP | Behavioral Health | Chuck | Catelyn | 2016-03-16 | 2016-03-23 |  | 2016-04-04 | 2016-04-07 |  | 2016-04-12 | 2016-04-16 | Operational | 2016-08-07 | 2016-09-08 |  | Credible
O000978 | True Care MD | HIE | Provider | Chuck/Ed/Lee | Brett | 2016-05-27 | 2016-05-31 |  | 2016-07-13 | 2016-08-01 | 2016-08-15 | 2016-08-19 | 2016-08-20 |  |  |  |  | Care Tracker
O000990 | United Community Health Center | HIE | FQHC | Chuck | Brett | 2016-02-08 |  |  | 2016-02-23 | 2016-03-03 |  | 2016-03-18 | 2016-03-23 |  | Not Ready BR 6/2 |  |  | NI
O000992 | Universal Care Management | HIE | Home Care | Chuck | Angell | 2016-01-14 |  |  | 2016-01-26 | 2016-01-26 |  | 2016-02-17 | 2016-04-04 |  |  |  |  | Case-e & Health Fusion
O000993 | University of Arizona Health Plan (UAHP) | HIE | Health Plan | Chuck | Brett | 2015-12-28 |  |  | 2016-01-07 | 2016-01-13 |  | n/a | n/a |  |  | N/A |  | NA
O001001 | Valle del Sol | PII/SHIP | Behavioral Health | Chuck | Catelyn | 2016-02-22 |  |  | 2016-03-09 | 2016-03-09 |  | 2016-03-10 | 2016-03-16 |  |  |  |  | NextGen(W/Topaz)
O001005 | Valley Anesthesiology | HIE | Specialty | Chuck | Brett | N/A | N/A |  | 2016-02-22 | N/A |  | N/A | N/A |  |  | N/A |  | NA
#N/A | Virginia G Piper (St. Vincent DePaul Clinics) | HIE | Provider | Chuck | Angell | 2015-12-17 |  |  | 2016-01-11 | 2016-01-21 |  | 2016-01-25 | 2016-02-04 |  | 42502 | 2016-06-08 |  | NI
O001041 | Wesley Community Health Center | PII | FQHC | Chuck | Catelyn | 2016-01-27 |  |  | 2016-02-17 | 2016-02-25 |  | Delayed | [5 empty] | e-Clinical Works
O001048 | West Yavapai Guidance Clinic | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-01 | 2016-07-05 |  | 2016-08-10 | 2016-08-12 | [7 empty] | NetsmartAvatar
#N/A | Wickenburg Regional Hospital | HIE | CAH | Chuck | Jaime | N/A | N/A |  | 2016-02-11 | 2016-02-25 |  | 2016-02-26 | 2016-02-29 |  | Delayed |  |  | CPSI/Greenway
#N/A | Yavapai County Detention Services | HIE | Corrections | Chuck | Brett | 2016-08-23 | 2016-08-23 | 2016-08-24 | 2016-09-12
O001077 | Yavapai Regional Medical Center | HIE | Hospital | Chuck | Brett | 2016-02-18 |  |  | 2016-03-16 | 2016-04-06 |  | 2016-05-06 | 2016-05-09 |  |  |  |  | Cerner/Millineum
O001081 | Youth Advocare Programs | HIE | Behavioral Health | Ed/Lee | Brett | 2016-07-01 | 2016-07-07 |  | 2016-08-02 | 2016-08-02 | Hold for BH Portal Data | [6 empty] | Netsmart My Evolve
O001083 | Yuma Children's Clinics - MSIC | HIE | Specialty |  | Ted | N/A | N/A |  | N/A | N/A |  | N/A | N/A |  |  |  |  | Epic
#N/A | Yuma Gastroenterology | HIE | Specialty | Chuck | Chuck | 2016-05-02 | N/A |  | N/A | 2016-05-10 |  | 2016-05-11 | 2016-05-11 |  |  |  |  | Epic/YMRC
#N/A | Yuma Hospital | HIE | Hospital |  | Ted | n/a |  |  | 2016-02-10 | N/A |  | N/A | N/A |  |  | N/A |  | Epic
#N/A | Yuma Nephrology, PC | HIE | Specialty | Chuck | Chuck | 2016-05-10 | N/A |  | N/A | 2016-05-11 |  | 2016-05-23 | 2016-05-24 |  |  |  |  | Epic/YRMC
#N/A | Zarephath | SHIP | Behavioral Health | Chuck | Moorthi | 2016-07-14 | 2016-07-18
Counts
| 191 | [7 empty] | 154 | 127 |  | 90 | 83
| NS |  | No Show |  | Green PM Until Assigned |  |  |  | Visit within 1 wk
| Follow Up on late draft roadmaps |  | Client Cancelled | [5 empty] | 2 weeks late
Completed Roadmap on hold
Delayed by Client

## Metrics
| Ted | Brett | Keith
Total | 12 | 70 | 0
Hospital | 5 | 3 | 0
CAH | 0 | 2 | 0
RHC | 0 | 1 | 0
Provider | 3 | 19 | 0
ACO | 0 | 2 | 0
FQHC | 1 | 2 | 0
Home Care | 0 | 2 | 0
Specialty | 2 | 6 | 0
Health Plan | 0 | 10 | 0
Behavioral Health | 0 | 7 | 0
RHBA | 0 | 3 | 0
State Gov't | 1 | 3 | 0